## Sheet1
S1 No | Name Of The Student | Year | Project Name | Start Date | Task | Month | Weekly Progress | Milestone | Status | Target Date | Remark
1 | Syed Saifulla H | 2026 | Microsoft Intune | 2026-01-10 | Study Of Intune Tool | January | WK1 | Initial Learning and Environment Setup | Completed | 2026-01-16 | Successfully understood Intune basics and set up test environment.
2 | Syed Saifulla H | 2026 | Microsoft Intune | 2026-01-18 | Study WinPak, Honeywell, Graph API, and Azure Cloud | January | WK2 | Understanding Integration Components | Completed | 2026-01-23 | Learned about WinPak access control system, Honeywell systems, Graph API for integration, and Azure cloud services.
3 | Syed Saifulla H | 2026 | Microsoft Intune | 2026-01-26 | Enrolled Devices and Testing and make POC | January | WK3 | POC Implementation and Testing | Completed | 2026-01-30 | Enrolled test devices (iOS and Android), configured policies, and tested POC for automated device restrictions based on physical access.